## Sheet1
Issue Identified | Action Taken | Timeline (Planned vs Actual) | Before Score/Status | After Score/Status | Improvement % | Evidence Link | Impact on Satisfaction/Performance
Limited library hours | Extended timings till 9 PM; weekend reading hall created | Planned: Jan 2024 → Completed: Feb 2024 | Library feedback: 3.6 | Library feedback: 3.9 | 8.3333 |  | Library usage increased by 35% during exams
Poor Wi-Fi in hostels | Upgraded from 50 Mbps → 200 Mbps; installed 5 routers | Planned: Jul 2023 → Completed: Aug 2023 | Wi-Fi feedback: 3.2 | Wi-Fi feedback: 3.7 | 15.625 |  | 50% fewer complaints; smoother LMS access
Outdated lab equipment | Procured 10 new lab kits; signed AMC for maintenance | Planned: Dec 2022 → Completed: Mar 2023 | Lab satisfaction: 3.9 | Lab satisfaction: 4.1 | 5.1282 |  | Improved practical learning outcomes
Lack of industry-ready skills | Introduced Data Science elective; organized workshops | Planned: Jun 2023 → Completed: Aug 2023 | Placement %: 72 | Placement %: 82 | 13.8889 |  | 15% rise in placements; better recruiter feedback